## Sheet1
Item | Due By
Ads |  | Need to determine final ad schedule & which content
Print Ads-Copy
Observer
|  |  | Gazette | Art due 5/14 | Art due 8/13 | Done-Kim
SW Bulletin
|  | Digital-Copy | FB | Need by 5/7 |  | Done-Kim
|  |  | Instagram | Need by 5/7 |  | Done-Kim
|  |  | Observer | Need by 9/1
Determine FB Ad Schedule
Medals | 2021-10-04 |  |  | Need final art by 5/30 |  | Kim/Bill
T Shirts | 2021-10-08 |  |  | Need final art by 5/30 |  | Kim/Bill
Posters | 2021-09-15 |  |  | Need final art by 9/1 |  | Kim/Bill
Banners | 2021-10-11
|  | Roundabouts |  | Art due 9/13 | Installed 10/1
|  | Building |  | Art due10/5 | Installed 10/15
PortaPotties
Table Covers
Awards
EMS
Sponsor Gifts
Food if Needed
Volunteers
Sponsors |  |  | First email went out; Several signed up already.
Will start sending regular emails end of month.
Runners |  |  | Email Deployments starting Memorial Day
Website |  |  | P&R | Done
|  |  | Run SignUp | Done